## Vplan
Total Items | 31 | Total testcases in Vplan
Pass Items | 2 | Status = Passed
Fail Items | 0 | Status = Failed
NY Items | 29 | NY = Not Yet run (default before regression)
Section | Main Title | Description | Testname | Priority | Method | Owner | Status | Milestone | Remark
1 | Register test
1.1 | Read default value | 1. Wait for reset (presetn) release and clocks stable 2. Read TCR(0x00), TSR(0x01), TDR(0x02), TIE(0x03) via APB Pass condition: TCR=8'h00, TSR=8'h00, TDR=8'h00, TIE=8'h00 (matching default value in RTL spec) | default_value_register_test | High | Directed | Quang | Passed
1.2 | Read and Write value check | 1. Write a walking-1/walking-0 and random pattern to every RW field: TCR[4:3] clk_div, TCR[2] load, TCR[1] count_down, TCR[0] timer_en, TDR[7:0] data, TIE[1:0] 2. Read back each register after each write Pass condition: Read data == written data on all RW bits; scoreboard matches reference model | rw_register_test | High | Directed | Quang | Passed
1.3 | Reserved bit / reserved region check | 1. Write 8'hFF to reserved bits TCR[7:5], TSR[7:2], TIE[7:2] 2. Write random data to reserved address region 0x04 -> 0xFF, then read back Pass condition: Reserved bits and reserved region read as 0; write does not affect any other register | reserved_region_test | High | Directed | Quang | Passed
1.4 | W1C attribute check (TSR) | 1. Trigger overflow/underflow so TSR[0]/TSR[1] are set by HW 2. Write 1'b0 to the set bit -> read back 3. Write 1'b1 to the set bit -> read back Pass condition: Write 0 does not clear (bit stays 1); write 1 clears the bit to 0; SW cannot set the bit by writing 1 when it is 0 | w1c_register_test | High | Directed | Quang | NY
1.5 | Reset on the fly check | 1. Configure all registers with non-default random values, start the timer 2. Assert presetn asynchronously at a random time Pass condition: All registers return to default value; counter = 0; interrupt = 1'b0 | reset_on_the_fly_test | High | Directed | Quang | NY
1.6 | APB protocol check | 1. Perform write/read transfers: IDLE -> SETUP (psel=1, penable=0) -> ACCESS (psel=1, penable=1) 2. Perform back-to-back transfers and transfers with idle gaps 3. Drive psel=0 with valid paddr/pwdata Pass condition: pready always 1 in ACCESS (no wait state); prdata valid in ACCESS phase; no register updated when psel=0 or penable=0 | apb_protocol_test | High | Directed | Quang | NY
1.7 | APB access while counting (CDC) | 1. Issue random APB reads/writes (TCR, TSR, TDR, TIE) while the counter is running, at each clk_div 2. Sweep the alignment between the APB access and the clk_in edge Pass condition: prdata is stable and correct (no metastability); counting is not disturbed by the access | cdc_access_while_counting_test | High | Random | Quang | NY
1.8 | Random register access / regression | 1. Randomize paddr (0x00->0xFF), pwrite, pwdata over N transfers, run with N different seeds Pass condition: All read/write behaviour matches the reference model (incl. reserved and W1C rules); all seeds pass and the functional coverage goal in the Coverage sheet is reached | random_register_test | Medium | Random | Quang | NY
2 | Clock divisor test
2.1 | No divide | 1. Set TCR.clk_div = 2'b00 while timer_en = 0, then set timer_en = 1 2. Sample clk_in and count the counter increment rate Pass condition: clk_in = ker_clk = 200 MHz; counter increments once per ker_clk cycle | clkdiv_no_divide_test | High | Directed | Quang | NY
2.2 | Divide by 2 | 1. Set TCR.clk_div = 2'b01 while timer_en = 0, then enable the timer Pass condition: clk_in = 100 MHz (1 count per 2 ker_clk cycles), 50% duty cycle | clkdiv_by2_test | High | Directed | Quang | NY
2.3 | Divide by 4 | 1. Set TCR.clk_div = 2'b10 while timer_en = 0, then enable the timer Pass condition: clk_in = 50 MHz (1 count per 4 ker_clk cycles) | clkdiv_by4_test | High | Directed | Quang | NY
2.4 | Divide by 8 | 1. Set TCR.clk_div = 2'b11 while timer_en = 0, then enable the timer Pass condition: clk_in = 25 MHz (1 count per 8 ker_clk cycles) | clkdiv_by8_test | High | Directed | Quang | NY
2.5 | Change clk_div between runs | 1. Run with clk_div = A, stop the timer (timer_en = 0) 2. Re-program clk_div = B (random A/B) and re-enable Pass condition: New divider takes effect on the next enable; no glitch on clk_in; counter keeps its previous value across the stop | clkdiv_reconfig_test | Medium | Random | Quang | NY
3 | Counter test
3.1 | Count up basic | 1. Program clk_div, count_down = 0, timer_en = 1 2. Observe the counter for M clk_in cycles Pass condition: Counter increments by 1 every clk_in rising edge and matches the reference model | count_up_test | High | Directed | Quang | NY
3.2 | Count down basic | 1. Program count_down = 1, timer_en = 1 Pass condition: Counter decrements by 1 every clk_in rising edge and matches the reference model | count_down_test | High | Directed | Quang | NY
3.3 | Load initial value from TDR | 1. Write initial value to TDR (random 8-bit) 2. Set TCR.load = 1 while timer_en = 0 3. Clear load and set timer_en = 1 Pass condition: Counter starts from the TDR value, not from 0 | load_counter_test | High | Directed | Quang | NY
3.4 | Load while counting | 1. Start the timer, let it count to a random value 2. Write TDR = random value, then set TCR.load = 1 Pass condition: Counter stops counting on load and is overwritten with the TDR data; counting resumes after load = 0 | load_on_the_fly_test | Medium | Directed | Quang | NY
3.5 | Timer enable / disable | 1. Enable the timer, count some cycles, then write timer_en = 0 2. Wait, then re-enable Pass condition: Counter freezes and holds its value while timer_en = 0; resumes from the held value when re-enabled | timer_enable_disable_test | High | Directed | Quang | NY
3.6 | Overflow rollover (255 -> 0) | 1. Load TDR = 8'hFD, count up until the counter passes 255 Pass condition: Counter wraps 255 -> 0 and continues counting; TSR.overflow is set on the transition | counter_overflow_test | High | Directed | Quang | NY
3.7 | Underflow rollover (0 -> 255) | 1. Load TDR = 8'h02, count down until the counter passes 0 Pass condition: Counter wraps 0 -> 255 and continues counting; TSR.underflow is set on the transition | counter_underflow_test | High | Directed | Quang | NY
3.8 | Change count direction | 1. Count up to a random value, set timer_en = 0 2. Set count_down = 1, re-enable the timer Pass condition: Counter continues from the held value in the new direction | count_direction_change_test | Medium | Directed | Quang | NY
3.9 | Continuous rollover | 1. Run the timer for several full 0 -> 255 -> 0 cycles (both directions) without clearing TSR Pass condition: Counter keeps counting correctly across repeated rollovers; status bit stays 1; no counter corruption | continuous_rollover_test | Medium | Directed | Quang | NY
3.10 | Counter random / stress | 1. Randomize clk_div, count_down, load, TDR and enable/disable timing over many iterations Pass condition: Counter value always matches the reference model; multiple overflow/underflow rollovers handled correctly | counter_random_test | Medium | Random | Quang | NY
4 | Interrupt test
4.1 | Overflow interrupt | 1. Set TIE.overflow_en = 1, count up to overflow (255 -> 0) Pass condition: TSR.overflow = 1 and interrupt output asserts and stays asserted until the status bit is cleared | overflow_interrupt_test | High | Directed | Quang | NY
4.2 | Underflow interrupt | 1. Set TIE.underflow_en = 1, count down to underflow (0 -> 255) Pass condition: TSR.underflow = 1 and interrupt asserts until the status bit is cleared | underflow_interrupt_test | High | Directed | Quang | NY
4.3 | Polling mode (interrupt disabled) | 1. Keep TIE = 8'h00, generate overflow and underflow 2. Poll TSR periodically Pass condition: TSR status bits still set by HW, but interrupt output stays 1'b0 | polling_mode_test | High | Directed | Quang | NY
4.4 | Interrupt clear by W1C | 1. Assert an interrupt (enabled), then write 1 to the corresponding TSR bit Pass condition: TSR bit clears and interrupt de-asserts; interrupt does not re-assert until the next overflow/underflow | interrupt_clear_test | High | Directed | Quang | NY
4.5 | Enable interrupt after status is set | 1. Generate overflow/underflow with TIE = 0 (status set, no interrupt) 2. Then write TIE.overflow_en / underflow_en = 1 Pass condition: Interrupt asserts as soon as enable is set while the status bit is still 1 (level-based enable) | interrupt_late_enable_test | Medium | Directed | Quang | NY
4.6 | Both overflow and underflow enabled | 1. Set TIE = 8'h03, generate an overflow then switch direction and generate an underflow 2. Clear only one status bit at a time Pass condition: Interrupt stays asserted while any enabled status bit is set; de-asserts only when all enabled status bits are cleared | interrupt_both_source_test | Medium | Directed | Quang | NY
4.7 | Status HW set vs SW clear race | 1. Align a write-1-to-clear on TSR with an HW overflow/underflow event, sweeping the alignment Pass condition: HW set has priority over the SW clear (no event is lost), per the reference model | status_set_clear_race_test | Medium | Random | Quang | NY
4.8 | Interrupt with clock divisor | 1. Repeat 4.1 / 4.2 with clk_div = 2'b01/2'b10/2'b11 Pass condition: Interrupt timing follows clk_in; CDC from clk_in domain to pclk domain is correct (no missed or duplicated interrupt) | interrupt_clkdiv_test | Medium | Random | Quang | NY

## Coverage
Covergroup | Coverpoint / Cross | Bins | Sampling event | Goal | Remark
cg_reg_access | cp_addr | TCR(0x00), TSR(0x01), TDR(0x02), TIE(0x03), reserved(0x04:0xFF) | APB ACCESS phase (psel & penable & pready) | 100%
cg_reg_access | cp_dir | write, read | APB ACCESS phase | 100%
cg_reg_access | cross cp_addr x cp_dir | all legal combinations | APB ACCESS phase | 100% | Ignore write to reserved region
cg_config | cp_clk_div | 2'b00, 2'b01, 2'b10, 2'b11 | TCR write | 100%
cg_config | cp_count_down | 0 (up), 1 (down) | TCR write | 100%
cg_config | cp_load | 0, 1 | TCR write | 100%
cg_config | cp_timer_en | 0->1 (start), 1->0 (stop) | TCR write | 100% | Transition bins
cg_config | cross cp_clk_div x cp_count_down | 8 combinations | timer_en rising edge | 100% | Key cross of the DUT
cg_counter | cp_cnt_value | 0, 1, low[2:126], mid[127], high[128:254], 255 | clk_in rising edge | 100%
cg_counter | cp_cnt_transition | 255->0 (overflow), 0->255 (underflow) | clk_in rising edge | 100%
cg_counter | cp_tdr_load_value | 8'h00, 8'hFF, random others | TCR.load = 1 | 100%
cg_interrupt | cp_tie | 2'b00, 2'b01, 2'b10, 2'b11 | TIE write | 100%
cg_interrupt | cp_status_src | overflow, underflow | TSR set by HW | 100%
cg_interrupt | cross cp_tie x cp_status_src | all combinations | TSR set by HW | 100% | Covers polling vs interrupt mode
cg_interrupt | cp_int_out | 0->1 (assert), 1->0 (clear by W1C) | interrupt signal change | 100%